OPERATIONS

# Studio Workflow and Quality SOP

How every Max_imum project runs from first message to final payment, so quality stays high as the studio grows.

## 1. The 8-step workflow

| Step | What happens | Document used | Target time |
| --- | --- | --- | --- |
| 1. Enquiry | Reply, ask the right questions, share rate card | Rate card, WhatsApp quick replies | Within 2 hours in working hours |
| 2. Brief | Client fills the creative brief | Creative Brief | 1 day |
| 3. Quote and contract | Send quotation with terms; client accepts; 50% deposit | Quotation, Terms or Agreement, Invoice | 1 day |
| 4. Concepts | Research, sketches, 2 to 3 concepts | Working Files folder | Per package |
| 5. Feedback | One combined round at a time; log each round | Revision log in Tracker | 3 working days per round |
| 6. Final files | Export, check quality, prepare delivery folder | Delivery checklist | 1 day |
| 7. Payment and handover | Balance paid; sign certificate; release files | Invoice, Receipt, Handover Certificate | Same day |
| 8. Follow-up | Thank you, ask for testimonial, portfolio consent, referral | Consent Form, Thank-you card | Within 7 days |

## 2. Folder structure (Google Drive)

Max_imum Designs / Clients / [Client name] / [YYYY]-[Project] /

- 00_Contract_and_Invoices (agreement, quote, invoice, receipt, certificate)

- 01_Brief_and_Client_Files (everything the client sends)

- 02_Research_and_References

- 03_Working_Files (layered files, sketches, unused concepts)

- 04_Proofs_Sent (every version sent for review)

- 05_Final_Delivered (the folder the client receives)

## 3. File naming

ClientName_Project_Item_vNN_YYYY-MM-DD.ext   Example: DukaPay_Logo_Horizontal_v03_2026-11-05.png. Final files drop the version number: DukaPay_Logo_Horizontal_Reversed.svg.

## 4. Quality checklist before sending anything

- Spelling, names, phone numbers, prices, dates and addresses checked twice (and by the client).

- Alignment, spacing and margins are consistent; text is readable at phone size.

- Colours checked against the brand palette and contrast (4.5:1 for body text).

- Fonts licensed and outlined or packaged; images licensed and credited where needed.

- Print files: CMYK or flagged RGB, 3 mm bleed, crop marks, 300 dpi, outlined text.

- Screen files: RGB, correct pixel size per platform, compressed for WhatsApp and web.

- AI-generated elements noted for the Handover Certificate.

## 5. Delivery pack

- Logo: PNG (transparent, white background), SVG, PDF, and AI or editable file if included.

- Brand kit: one-page brand sheet or full guidelines PDF, fonts list, colour codes (HEX, RGB, CMYK).

- Social: PNG at platform sizes; editable templates if included.

- Print: print-ready PDF with bleed, plus screen-size JPG.

- A short "how to use your files" message and a reminder of the 14-day correction period.

## 6. Protect the work

- Backup rule 3-2-1: 3 copies, 2 types of storage, 1 off-site (cloud). Back up at the end of each day you work.

- Two-step verification on email, Drive, WhatsApp, Instagram and the bank.

- Release final files only after full payment. Send low-resolution or watermarked previews for unpaid work.

- Keep a log of every revision round (date, request, done). It prevents disputes.

## 7. Communication standards

- Reply to every message within 24 hours (2 hours during business hours for new enquiries).

- Confirm every request in writing: "Got it. I will send the update by [day]."

- Say no politely to out-of-scope work and send a quote.

- Weekly Friday check-in message for longer projects.

## 8. Monthly business review (30 minutes)

- Income, expenses and money owed. Did each job meet your target hourly rate?

- New enquiries versus won projects (conversion rate).

- Best and worst jobs: what to repeat, what to price higher or stop.

- One thing to improve in the portfolio, website or processes.